## Cable Tray Checklist
EPC Cable Tray Installation Checklist
Stage | Checklist Item | Best Practice / Requirement | Status (✓/✗) | Remarks
Design Phase | Tray Type Selection | Choose ladder, perforated, solid-bottom, or wire mesh based on load, environment, and signal sensitivity.
| Segregation Plan | Separate trays for power, instrumentation, and communication cables; maintain spacing as per IEC/NEC.
| Spare Capacity | Design trays with 30–40% spare space for future expansion.
| Fire & Hazardous Area Compliance | Use fire-rated trays and ATEX/IECEx-approved materials in hazardous zones.
| Routing & Layout | Avoid sharp bends, congestion, and interference with HVAC/piping.
| Structural/Seismic Load | Ensure support design meets seismic/structural load requirements.
Material Procurement | Tray Material | Select hot-dip galvanized, epoxy-coated, stainless steel, or FRP based on environment.
| Covers & Accessories | Provide solid/vented covers, grommets, and protective linings for outdoor/harsh conditions.
| Hardware Quality | Use corrosion-resistant fasteners, clamps, and brackets.
Installation Phase | Support Spacing | Install supports every 1.5–2 m (as per tray type and load).
| Earthing & Bonding | Ensure continuous electrical bonding across tray sections; comply with IEC 61537/NEC 392.
| Expansion Joints | Provide expansion joints/flexible couplings in long runs or high-temperature zones.
| Cable Grouping & Tagging | Maintain orderly routing, bundle conductors, and label cables for identification.
| Moisture Management | Provide drainage holes/sloping in outdoor trays; prevent water pooling.
| Vibration Control | Use vibration isolation supports near rotating equipment.
Inspection & Commissioning | Quality Check | Verify mechanical strength, alignment, grounding, and bonding.
| Fill Factor | Ensure trays are not filled beyond 70% of capacity.
| Documentation | Update as-built drawings, tagging, and digital layout (BIM/3D).
| Safety Verification | Confirm compliance with NEC, IEC, and project specifications before handover.
Operation & Maintenance | Routine Inspection | Check for corrosion, loose fasteners, sagging, damaged cables.
| Preventive Maintenance | Clean trays, check bonding, replace damaged parts periodically.
| Digital Monitoring | (Optional, modern EPC) Use sensors or digital twin for cable health and tray integrity tracking.
Done by
Verified by