## Fire Alarm Method Statement
METHOD STATEMENT – ADDRESSABLE FIRE ALARM SYSTEM INSTALLATION, TESTING & COMMISSIONING (NFPA 72)
Phase | Activity Category | Activity Description | System / Device Type | Loop / Zone / Area | NFPA / Spec Reference | Inspection / Test Method | Acceptance Criteria | Cable Type / Rating | Responsible Discipline | Inspection Status | Verified By | Date | Remarks
Engineering | Design Review | IFC fire alarm layout drawing approved | System | All Areas | NFPA 72 | Document review | Approved IFC available | - | F&G / Instrument
Engineering | Design Review | Loop wiring diagrams reviewed (Class A) | SLC Loop | All Loops | NFPA 72 | Document review | Approved diagrams | - | F&G / Instrument
Engineering | Design Review | Cause & Effect matrix approved | System | All Zones | Project Spec | Document review | Approved matrix | - | F&G / Instrument
Material | Inspection | FACP model and rating verified | FACP | Control Room | Approved Submittal | Visual / Datasheet | Correct model installed | - | Instrumentation
Material | Inspection | Fire-rated cable compliance verified | Cables | Cable Trays | Project Spec | Visual / Certificate | Fire-rated cable used | FRLS / Fire Resistant | Instrumentation
Installation | Panel Installation | Fire alarm control panel mounted at approved location | FACP | Control Room | NFPA 72 | Visual inspection | Panel accessible & secured | - | Instrumentation
Installation | Wiring | Class A SLC loop wiring completed | SLC Loop | All Loops | NFPA 72 | Visual / Continuity test | Loop continuity achieved | Twisted Pair FRLS | Instrumentation
Installation | Device Installation | Smoke detectors installed as per spacing requirements | Smoke Detector | Process Areas | NFPA 72 | Measurement | Spacing compliant | - | Instrumentation
Installation | Device Installation | Manual call points installed at exits | MCP | Escape Routes | NFPA 72 | Visual / Measurement | Height & location compliant | - | Instrumentation
Testing | Pre-Commissioning | Loop continuity test performed | SLC Loop | All Loops | NFPA 72 | Multimeter | Continuity OK | - | Commissioning
Testing | Pre-Commissioning | Insulation resistance test performed | Cables | All Loops | Project Spec | IR Tester | IR > Specified value | - | Commissioning
Testing | Functional Test | Smoke detector functional test | Smoke Detector | Zone-wise | NFPA 72 | Test aerosol | Alarm generated correctly | - | Commissioning
Testing | Functional Test | Sounder / speaker audibility test | Notification | All Zones | NFPA 72 | Sound level meter | Audible as required | - | Commissioning
Commissioning | System Integration | Cause & effect verification completed | System | All Zones | Project Spec | Simulation test | Outputs operate correctly | - | Commissioning
Commissioning | Final Test | Battery backup duration test | Battery | Panel | NFPA 72 | Power failure simulation | Backup time achieved | - | Commissioning
Handover | Documentation | As-built drawings submitted | Documents | System | Project Spec | Document check | Approved as-built | - | Instrumentation
Handover | Training | Operator training completed | System | Control Room | Project Spec | Training record | Operators trained | - | Instrumentation