## FRL Checklist
ADVANCED ENGINEERING WORKBOOK ¦ FRL UNIT SELECTION & COMMISSIONING CHECKLIST
| Completion % |  | Done Items |  | Open Items |  | High Risk |  | Avg Score
| 0% |  | 0 |  | 36 |  | 27 |  | 0
ENGINEERING CHECK MATRIX
ID | Section | Checklist Item | Technical Requirement / Acceptance Criteria | Verification / Evidence | Status | Priority | Risk | Owner | Due Date | Remarks | Score
FRL-01 | Valve/Actuator Data | Confirm actuator type | Spring return or double acting identified from datasheet | Review datasheet | Not Started | High | 3 |  |  |  | 0
FRL-02 | Valve/Actuator Data | Confirm fail action | Fail open / fail close / fail in place verified | Review datasheet | Not Started | High | 3 |  |  |  | 0
FRL-03 | Valve/Actuator Data | Confirm required operating pressure | Operating pressure within actuator and regulator capability | Compare datasheet vs. project requirement | Not Started | High | 3 |  |  |  | 0
FRL-04 | Valve/Actuator Data | Confirm stroke time | Required stroke time defined and achievable | Stroke time spec / calculation | Not Started | High | 3 |  |  |  | 0
FRL-05 | Air Supply | Check instrument air header pressure | Header pressure available with adequate margin above setpoint | Plant air header reading | Not Started | High | 3 |  |  |  | 0
FRL-06 | Air Supply | Check dew point | Air dew point suitable for service and ambient temperature | Instrument air test record | Not Started | High | 3 |  |  |  | 0
FRL-07 | Air Supply | Check moisture carryover | No unacceptable liquid carryover to FRL | Inspection / drain history | Not Started | High | 3 |  |  |  | 0
FRL-08 | Air Supply | Check oil carryover | Oil level within acceptable instrument air quality limits | Air quality test / vendor limit | Not Started | Medium | 2 |  |  |  | 0
FRL-09 | Air Supply | Check particulate contamination | Air line clean and free of rust, dust, scale | Line cleanliness / filter inspection | Not Started | Medium | 2 |  |  |  | 0
FRL-10 | Sizing | Calculate actuator air consumption | Air volume and cycle demand determined | Actuator volume calculation | Not Started | High | 3 |  |  |  | 0
FRL-11 | Sizing | Verify simultaneous demand | Branch line can support multiple simultaneous valve strokes if applicable | Network review | Not Started | Medium | 2 |  |  |  | 0
FRL-12 | Sizing | Verify safety margin | Sizing includes margin for filter loading and line losses | Calculation margin check | Not Started | High | 3 |  |  |  | 0
FRL-13 | Regulator | Select correct pressure range | Setpoint sits near mid-range of regulator adjustment band | Vendor data / setpoint review | Not Started | High | 3 |  |  |  | 0
FRL-14 | Regulator | Verify droop performance | Acceptable pressure droop under dynamic demand | Vendor curve / test | Not Started | High | 3 |  |  |  | 0
FRL-15 | Regulator | Verify flow capacity | Regulator capacity exceeds actuator demand | Vendor flow chart | Not Started | High | 3 |  |  |  | 0
FRL-16 | Filter | Select filter type | Standard or coalescing element selected based on air quality | Vendor selection | Not Started | High | 3 |  |  |  | 0
FRL-17 | Filter | Select filter rating | Micron rating appropriate for downstream solenoid/actuator | Datasheet / standard | Not Started | High | 3 |  |  |  | 0
FRL-18 | Filter | Check bowl drainage | Drain arrangement appropriate for condensate generation | Inspection / selection | Not Started | High | 3 |  |  |  | 0
FRL-19 | Filter | Verify pressure drop | Filter pressure drop acceptable at required flow | Vendor curve | Not Started | Medium | 2 |  |  |  | 0
FRL-20 | Lubricator | Confirm lubrication is required | Do not install lubricator unless manufacturer approves or requires it | Manufacturer recommendation | Not Started | High | 3 |  |  |  | 0
FRL-21 | Lubricator | Verify oil compatibility | Any selected lubricant is compatible with all downstream components | Vendor approval | Not Started | High | 3 |  |  |  | 0
FRL-22 | Drain | Select drain type | Manual / semi-auto / auto drain matches access and moisture load | Layout review | Not Started | High | 3 |  |  |  | 0
FRL-23 | Drain | Verify drain maintainability | Drain can be inspected and serviced safely | Field access check | Not Started | Medium | 2 |  |  |  | 0
FRL-24 | Environment | Assess installation location | Indoor / outdoor / coastal / dusty / corrosive environment reviewed | Site inspection | Not Started | High | 3 |  |  |  | 0
FRL-25 | Environment | Confirm materials of construction | Body, bowl, seals and gauge suitable for environment | Vendor materials review | Not Started | High | 3 |  |  |  | 0
FRL-26 | Environment | Confirm protection class | Protection and corrosion resistance adequate | Project spec review | Not Started | Medium | 2 |  |  |  | 0
FRL-27 | Installation | Verify flow direction | Installed in correct orientation per manufacturer | Field check | Not Started | High | 3 |  |  |  | 0
FRL-28 | Installation | Verify access to gauge | Gauge visible after installation | Walkdown | Not Started | Medium | 2 |  |  |  | 0
FRL-29 | Installation | Verify access to drain | Drain accessible for operation and maintenance | Walkdown | Not Started | Medium | 2 |  |  |  | 0
FRL-30 | Installation | Verify upstream isolation valve | Isolation valve provided for maintenance | P&ID / field check | Not Started | High | 3 |  |  |  | 0
FRL-31 | Commissioning | Perform air line cleanliness check | Purge completed; debris / moisture removed | Purge record | Not Started | High | 3 |  |  |  | 0
FRL-32 | Commissioning | Leak test complete circuit | No leakage on tubing, fittings or FRL body | Leak test record | Not Started | High | 3 |  |  |  | 0
FRL-33 | Commissioning | Set regulator pressure | Final setpoint recorded and verified under load | Commissioning record | Not Started | High | 3 |  |  |  | 0
FRL-34 | Commissioning | Stroke valve fully | Open/close operation confirmed with physical observation | Functional test | Not Started | High | 3 |  |  |  | 0
FRL-35 | Commissioning | Confirm fail position | Fail open/close action correct during loss of air/power test | Functional test | Not Started | High | 3 |  |  |  | 0
FRL-36 | Maintenance | Record spare parts | Filter elements, seals, gauge and drain kits identified | Spare parts list | Not Started | Medium | 2 |  |  |  | 0
FRL-37 | Maintenance | Verify preventive maintenance plan | Inspection and drain schedule defined | PM plan | Not Started | Medium | 2 |  |  |  | 0
FRL-38 | Documentation | Capture final configuration | Filter type, drain type, setpoint, and notes logged | As-built / dossier | Not Started | Medium | 2 |  |  |  | 0
Engineering note: prioritize clean dry air, correct flow capacity, and manufacturer-approved lubrication strategy. FRL selection is part of reliability planning, not a minor accessory.